Guideline

for the strategic planning of a learning outcome-based TCA event

Outcome based strategic planning of TCA-s
TCA lifecycle ADVANCED
Peer Learning Activity

Mondolat Consulting Ltd.

Budapest, 29 November 2019

Content

1	Introduction	3

2	The TCA activity	3

3	The process of strategic planning of a TCA event	4

3.1	Setting goals	5

3.1.1	Review of strategic goals	5

3.1.2	Choosing the appropriate strategic goal	7

3.1.3	Conducting a Needs Analysis	7

3.1.4	Identifying development objectives as a basis for the prospective TCA project	8

3.2	Conducting Resource Analysis	9

3.2.1	Internal human resources	9

3.2.2	External human resources	9

3.2.3	Other resources	9

3.3	Defining learning outcomes for prospective TCA project	11

3.4	Definition of criteria for selection of participants	14

3.4.1	Identifying selection criteria for expected participants	14

3.4.2	Elaborate methods for evaluating participants’ applications	15

3.4.3	Carrying out the selection process of the participants	15

4	Drawing up a TCA project plan	15

5	Guarantees of a successful TCA project	17

Introduction

This guideline is the outcome of the Peer Learning Activity (hereinafter PLA)  for TCA officers organized by the Tempus Public Foundation on 29th of October 2019 on Outcome based strategic planning of Transnational Cooperation Activities (hereinafter TCAs)  . The findings of the workgroups on this PLA were used as good examples for this guide thus special  thanks to the following  table hosts who coordinated the workgroups as well as to the participants for their contributions.

Table 1:		Impact – Carmel Welsh (IE) Ildikó Gulácsi (HU)

Table 2:		Internationalization of HE and VET institutions – Ingrid Gran (SE)

Table 3:		Professionalization of teachers and staff - Judith Dayus-Brouwer (NL)

Table 4:		Inclusion - Monika Held (DE)

The guide aims to briefly summarize the key concepts and techniques of the strategic planning of a learning outcome-based TCA project for the hosting organisations. All the examples listed in the tables bellow are from the PLA mentioned above.

The TCA activity

Two types of TCAs the  Transnational training, support and contact seminars of potential Erasmus+ Programme participants (TSS) and the Transnational thematic activities linked to the objectives, priority target groups and themes of the Erasmus+ Programme (THO)

can be considered as a project, that is why we must first define the concept of a project. A project is a unique, complex process system consisting of a group of activities undertaken, coordinated, and controlled to meet specific requirements (including time, cost, and resource constraints) with set start and end dates.

A TCA project is a way of accomplishing tasks that cannot be classified as regular and recurring activities of the National Agencies (hereinafter NA).

Features of a good project:

- relevant

- demand-driven, therefore it is based on needs;

- goal-oriented: it moves towards product creation;

- it is linked to and meets the strategic goals of the organisation.

- feasible

- well thought out, consistent;

- it has measurable results;

- it has a realistic budget;

- clear division of labour among project implementers;

- the risks and areas of uncertainty are known and specific, and well thought out measures are available to address them.

- sustainable

- the exploitation of its results is ensured even after the project is closed.

The process of strategic planning of a TCA event

A TCA project can only be considered successful if it has fully achieved its objectives, so it is essential for the project objectives to be precisely defined. The identification of the objectives happens during the definition phase of the project. Therefore, before setting goals, it is imperative that  the TCA officer reviews the strategic goals of the NA and, based on them, defines the development objectives of it, which, once agreed within the NA and  with partners, can become the basis for the official project objective.

In any case, a project goal must be specific, accessible, measurable, relevant and timely, and time bound. This is highly important because it is easier to assign learning outcomes (expected results) to well-formulated project objectives. The use of learning outcomes helps to determine when a given objective can be considered to have been achieved. For measuring the expected learning outcomes, it is necessary to design indicators. It is important to note that without having defined clear TCA objectives and expected learning outcomes  (and indicators for assessment ), it is strictly forbidden to plan any activity.

The following table illustrates the logic of TCA project planning:

Strategic goals

Development and project objectives

Expected learning outcomes

Indicators (measurable )

PLANNING

(activities, resources, risks, etc.)

Setting goals

Goals are specific expectations set by the organisation that enable the organisation to fulfil its mission and realize its vision. The goal is a desirable, attainable and determined state.

Goal setting is one of the most difficult tasks for an organisation. The SMART method helps to formulate the goals. All goals must meet the following requirements:

- Specific–specific quantity and quality;

- Measurable–in an objective way;

- Achievable;

- Relevant–relevant, selective, independent;

- Time-based.

Goals are built on each other and can be deduced from one another. This is called target hierarchy. There are basically three types of goals that can be distinguished:

- Strategic goals: Expectations related to general, higher-level expected results;

- Development objectives: Short-, medium-, or long-term goals related to the operation of the institution which can be derived from strategic goals and contribute to their achievement;

- Project objectives: Short-, medium-, or long-term goals for a given development that are project-based. The project objectives are also in line with the strategic objectives of the institution as they are derived from development objectives. Development project objectives should be reflected in the action plan of the TCA project.

Review of strategic goals

Strategic goals are comprehensive yet well-graspable. Concise goals are formulated in one or two sentences. They are based on the mission of the organisation and respond to the identified challenges in its operational environment. Strategic goals should be set at the highest level of abstraction, which means that relatively few (3-5) goals are sufficient for the organisation. Keep in mind that the strategic documents may already contain strategic and development goals, so it is worth reviewing those document first.

Strategic goals are not necessarily long-term goals. For example, strengthening the National Agency’s international reputation is an objective that can be assigned as a short-, medium-, or long-term goal.

First the TCA officer must determine which of the existing institutional or other documents can be considered as strategic documents and must also identify other documents that contain strategic objectives or plans as well as the ones that may be related to the institutional strategy.

Possible sources of strategic goals

Strategic goals can be found in the following documents:

Strategic goals at European level:

- Europe 2020 strategy;

- Council recommendations and Commission initiatives related to European Education Area 2025;

- Strategic goals of current and upcoming Erasmus+ programmes

Strategic goals of NA:

- mission statements;

- NA general strategies developed for the work programme that include Needs Analysis;

- TCA objectives in the work programme.

Strategic priorities for TCAs proposed by NA directors

The directors of NAs–at their informal meeting in Malta in 2017–discussed the objectives of  transnational cooperation activities and took stock of the strategic priorities of all NAs. The most prioritised topics were clustered to four main broad themes which were coined as the four priority themes for transnational cooperation activities. These priority themes–impact, internationalization of HE and VET institutions, professionalization of teachers and staff and inclusion–provide  strategic focus for the TCAs in 2018-2020. The priorities are not exclusive, other topics can also be proposed. The priority themes include different subtopics, some examples are presented below as can be seen on the SALTO E&T platform.

Impact

- Supporting KA2 projects on dissemination and sustainability;

- Promoting cross-sectoral exchange of practice;

- Capacity building in impact and dissemination;

- Evidence based methods and tools on impact.

Internationalization of HE and VET institutions

- European internationalisation strategies within VET and HEI;

- Internationalisation strategies for VET Charters;

- Long term pupil mobility;

- Student recognition.

Professionalization of teachers and staff

- International project management skills;

- Validation of learning experiences;

- 21st century skills;

- Interactive teaching methodologies.

Inclusion

- Equal opportunities in education;

- Supporting migrants through education and training;

- 21st century skills (especially critical media and digital competences);

- Erasmus+ Role Models.

Upon reviewing the priority themes the  most important development objectives for the future TCA can be identified.

The following examples illustrate this process:

| Priority | Possible development objectives |
| --- | --- |
| Impact | Supporting education in different fields |
|  | Increasing the quality of Erasmus+ programme results |
|  | Building new partnerships |
|  | Improving the quality of Erasmus+ on system level |
|  | Reaching newcomers for Erasmus+ programme |
|  | Studying the impact of hosted mobility in HE (2020) |
| Internationalization of HE and VET institutions | Increasing the quality of Erasmus+ projects |
|  | Sharing internationalisation strategies in VET |
| Professionalization of teachers and staff | Increasing the number of participants |
|  | Increasing the quality of projects |
| Inclusion | A broader understanding of the concept of inclusion by the participants |
|  | Using Erasmus+ as an instrument for inclusion |

Choosing the appropriate development objective

The diversity of the above sources shows that it is not easy to select the development objective that will serve as the basis for the future TCA projects. So, it is essential to find the development objective that is the most appropriate for organizing the next TCA project.

Conducting a Needs Analysis

Once the actual development objective has been identified, it is useful to conduct a Needs Analysis to reinforce the possible development objectives with this bottom up approach. There are two ways of conducting a Needs Analysis. In chapter 3.1.1 and 3.1.1.1 we gave an example of the

Top-down approach:	Looking at the national priorities, work plan, etc.

European policies

National policies

Commission feedback

Bottom-up:	Feedback from beneficiaries, analysis of actual activities on the ground, main issues, and participants’ need for provision of information, etc.

Possible tools:

- surveys among beneficiaries;

- trend analyses of former TCAs:

- applications;

- applicators;

- sector analyses;

- etc.

An overview of previously implemented TCAs is a must in identifying needs.

Whichever method is chosen, it is essential to always determine needs based on valid data.

Identifying development objectives as a basis for the prospective TCA project

A strategic goal can have several development objectives. This is important because the development directions defined by the strategic goals will be specified by the development objectives, to which (expected) results can be assigned by indicating the time span (short, medium, long term).

| Priority | Possible development objectives |
| --- | --- |
| Impact | Increasing the quality of Erasmus+ programme results |
|  | Focusing on (reaching and teaching) newcomers |
|  | Increasing the quality of newcomers engaging in Erasmus+ programme |
| Internationalization of HE and VET institutions | Provision of information, general and targeted promotion (e.g. identification of multipliers) |
|  | Clarification of concepts for participants |
|  | Supporting applicants to complete and verify the application form |
| Professionalization of teachers and staff | Increasing the number of participants |
|  | Increasing the competences of participants |
|  | Supporting the capacity building of the participants |
| Inclusion | Enhancing higher participation of schools with a higher number of disadvantaged students |
|  | Increasing the number of peer learning activities |
|  | Developing resources and expert pool on different subjects (3 years) |

Similar to the method used for strategic goals, it is advisable to first select several (maximum three) development objectives, then narrow down the scope and keep the one that best suits the NA. This will be the basis for defining the specific project objective.

Conducting Resource Analysis

In order to select the most appropriate project objective, it is worth examining which internal and external resources can ensure the most effective (and most efficient) implementation of the TCA project we are planning. In addition to the resources listed below, the TCA officer should always consider the budget available for the project.

Internal human resources

The availability of internal resources depends entirely on the organisation where the TCA officer works. The  TCA officer is one of the main internal resources, but of course they cannot do all the tasks, so they need to involve competent colleagues.

Possible internal human resources for a prospective TCA project:

- NA officer (with knowledge on the type of projects, e.g. inclusion)

- Communication/PR officer

- Officer from the financial department

- Colleagues working on the theme and/or in the sector

- Responsible person for the content of the planned event

- Responsible person for logistics, administration

- Event manager

- Keynote speakers, trainers, facilitators (they could be external resources as well)

External human resources

After examining internal resources, the resources that are not available in the organisation can also be identified.

Possible external human resources for a prospective TCA project:

- Colleagues form other NAs

- Keynote speakers, trainers, facilitators (they could be internal resources as well)

- Experts

- Representatives of professional organisations or associations

Other resources

- Project management tools, e.g. Trello

- Salto Resource Centre

- Relevant websites

- Good practice repositories

- Documentation of previously completed TCA projects

After listing the potential resources, a TCA official has all the relevant information to set a specific project objective to meet the development objectives and strategic goals as well.

The following figure shows the target hierarchy:

| Priority | Strategic goals | Development objectives | Project objectives |
| --- | --- | --- | --- |
| Impact | Supporting education in different fields | Increasing the quality of Erasmus+ programme results | ? |
|  | Increasing the quality of programme results | Focusing on (reaching and teaching) newcomers |  |
|  | Building new partnerships | Increasing the quality of newcomers engaging in Erasmus+ programme |  |
|  | Improving the quality of Erasmus+ on system level |  |  |
|  | Reaching newcomers for Erasmus+ programme |  |  |
|  | Studying the impact of hosted mobility in HE (2020) |  |  |
| Internationalization of HE and VET institutions | Increasing the quality of Erasmus+ projects | Provision of information, general and targeted promotion (e.g. identification of multipliers) | The professionalization of teachers |
|  | Sharing internationalisation strategies in VET | Clarification of concepts for participants |  |
|  |  | Supporting applicants to complete and verify the application form |  |
| Professionalization of teachers and staff | Increasing the number of participants | Increasing the number of participants | Developing competences of participants (development of project ideas; applying for a project; project management competences; intercultural competences) |
|  | Improving the quality of projects | Increasing competences of participants |  |
|  |  | Supporting the capacity building of participants |  |
| Inclusion | Raising awareness among participants of a broader understanding of inclusion | Enhancing higher participation of schools with a higher number of disadvantaged students | Higher participation of schools with a higher number of disadvantaged students–PLA, long term activity (3 years). |
|  | Using Erasmus+ as an instrument for inclusion | Increasing the number of peer learning activities |  |
|  |  | Developing resources and expert pool on different subjects (3 years) |  |

Defining learning outcomes for prospective TCA project

Remember, a TCA project can only be successful if the measurable learning outcomes are well-defined.

The learning outcomes approach focuses on  learner, where the learning process itself and the learner's competence development are essential.

Benefits of using learning outcomes:

- Better alignment of participants' needs (knowledge, skills and competences) with TCA services

- Learning outcomes provide clear information to potential participants and help them to decide whether to attend the TCA event

- drafting expected Learning outcomes make TCA planning, content, and requirements more consistent

- Allows for a more objective evaluation of the TCA event, as it is easier to develop evaluation criteria to concrete expected learning outcomes,

- Learning outcomes allow for individual learning pathways

Learning outcomes can be described by the following descriptors based on the European Qualification Framework.

- Knowledge (cognitive)

Cognitive elements, a set of facts, principles, and theories related to a work area, typically the possession of professional knowledge.

- Skill

Ability to apply knowledge and use know-how to complete tasks and solve problems; action-level knowledge, typically professional skills, but also dexterity and the use of and methods, materials, tools, or equipment.

- Competence

Perceptual issues related to profession, work, professional attitudes, views and behaviours such as: open, curious, interested, willing / willing to do something (e.g. collaborative), etc.

Each activity is characterized by the degree of autonomy and responsibility that a person can perform.

Competence can be understood as actually achieved learning outcomes, validated through the ability of the learner to autonomously apply knowledge and skills in practice, in society and at work. Learning outcomes are validated by their relationship to competences.

The potential learning outcomes of the objectives of the above TCA projects are summarized in the following table:

| Learning outcomes | Priorities |  |  |  |
| --- | --- | --- | --- | --- |
|  | Impact | Internationalization | Professionalization | Inclusion |
| Knowledge | Participants will be aware of how to use impact as a phenomenon in evaluating their KA1 projects | Participants will know the requirements of Erasmus+ applications | Participants will know the project life cycle | Participants will know how to use KA1 and KA2 projects in the field of SE and VET as a tool for inclusion |
|  | Participants will know how to connect their organisation's goals to EU policies | Participants will be aware of the opportunities offered by the Erasmus + program | Participants will know Erasmus+ rules and NA regulations | Participants will know how to strategically plan an inclusion project |
|  | Participants will understand the framework of KA1 | Participants will know the funding mechanisms | Participants will know through which channels they can search for project partners | Participants will learn about successful ways to collaborate with disadvantaged students |
|  | Participants will understand the requirements of successful Erasmus+ applications/projects | Participants will know the eligibility criteria for the application |  |  |
|  | Participants will know good practices | Participants will know the evaluation criteria for the different parts of the application form |  |  |
|  |  | Participants will know the resources that contain good practices from ongoing and past programs |  |  |
|  |  | Participants will be aware of information about potential partners |  |  |
| Skills | Participants will be able to use the Impact+ or other similar tools | Participants will be able to communicate their project messages in the language of the application form | Participants will have a higher level of language skills | Participants will be able to apply new teaching methods in the school |
|  | Participants will be able to design their own projects | Participants will be able to formulate the needs in an application form | Participants will be able to write an appropriate application | Participants will be able to formulate project proposals and fill in the application form |
|  | Participants will be able to manage their own projects | Participants will be able to explain why that project was chosen and how they want to implement it. | Participants will be able to formulate the content of their application |  |
|  | Participants will be able to use the application process as a tool in quality assurance of their KA1 projects | Participants will be able to form and submit their own application | Participants will be able to work in a multicultural environment |  |
|  | Participants will be able to plan the budget of their own project | Participants will be able to perform a Needs Analysis and develop a appropriate European Development Plan | Participants will be able to use technics of budget management |  |
|  |  |  | Participants will be able to manage the entire project cycle |  |
|  |  |  | Participants will be able to use Mobility Tool + at a high level |  |
| Competences | Participants will be conscious of strategic thinking | Participants will be familiar with the 'learn to learn' process | Participants will apply strategic thinking in the preparation of their application | Participants will be able to use the concept of strategic planning of an Erasmus+ project |
|  | Participants will be committed to use quality management tools | Participants will be able to independently build networks to prepare and implement their own projects | Participants will be able to solve problems on their own | Participants will be able to consciously plan the dissemination of experience to other teachers or stakeholders or potential applicants. |
|  |  | Participants will consciously use their medium / long term planning ability | Participants will be able to carry out self-assessment independently |  |
|  |  |  | Participants will be able to take responsibility for their decisions |  |
|  |  |  | Participants will be able to actively operate their own network |  |
|  |  |  | Participants will be able to analyse their own strengths and weaknesses independently |  |

The TCA project will only achieve its objective if the participants have acquired the defined learning outcomes. For this reason, it is imperative that the TCA officer defines the criteria and the way in which learning outcomes are evaluated.

Evaluation is an integral part of the learning-teaching process, so the evaluation process and all its elements need to be planned before the event, in preparation for the TCA project. The evaluation criteria must be closely linked to the learning outcomes.

Some evaluation principles:

- The trainers or the tutors must evaluate realistically, and objectively.

- During the evaluation, uniform procedures and conditions must be ensured for all participants.

- Evaluation and self-evaluation are only effective if participants can present themselves, their learning outcomes, and the characteristics of their learning in real-life situations and in diverse contexts.

- Therefore, during evaluation the participants’ strengths should be emphasised.

Information from a well-conducted evaluation may form the basis for a subsequent impact assessment.

Definition of criteria for selection of participants

After having set the objectives of the TCA project and the expected results (learning outcomes), concrete activities can begin. The first step is to select the appropriate participants.

Identifying selection criteria for expected participants

It is the responsibility of the hosting NA to clearly define the profile of participants and it is the responsibility of the sending NA to respect those specifications. For example, if the receiving NA requests experienced beneficiaries, the sending NA should refrain from sending a newcomer or a person with limited experience. Therefore, it is important to respect the decision of the sending NA with regards to the participants’ selection. They should make the final decision not the hosting NA.

The most important step is to identify the target group, which can be done according to the following criteria:

- Prior experience of participation in Erasmus + programme (or newcomer, depending on the objective of the TCA)

- Relevant language skills for the topic of the TCA project (ability to communicate fluently in the working language)

- Level of knowledge depending on the activity and topic of the TCA project

- Motivation to participate in Erasmus+ programme

- Motivation to participate in the TCA project (how will the prospective participants use the information provided by the TCA project?)

- The ability or willingness to disseminate the results of the TCA project

If the TCA officer already knows which sending NAs they can think of based on previous collaborations, they might want to consult the criteria beforehand to ensure they have the right number of participants.

Elaborate methods for evaluating participants’ applications

It is important that, just like with designing the learning outcomes, the evaluation of the applications should be planned. These evaluation criteria should also be sent to the sending NAs so that they can clearly see the expectations and inform the applicants about them. The selection process and its results should be published.

Carrying out the selection process of the participants

The sending NA must communicate the call directly to the potential beneficiaries/participants on the basis of selection criteria defined by the hosting NA. It is crucial that the sending NAs should carry out the selection process since they fund their participants, and of course the country specific regulations and Erasmus+ priorities–for example regional balance–must also be respected.

The sending NA must then select the participants according to the criteria set by the hosting NA. (Sometimes, there could be very good applications, but not relevant to the particular topic of the TCA project. Such applications should be kept for the future or be referred to other TCA opportunities.)

It is also possible that applicants submit an appropriate application form, but a personal meeting may reveal that they are still not eligible for the planned TCA project. Therefore, if possible, it is worth arranging in-person meetings with the applicants.

Drawing up a TCA project plan

The purpose of this guide is to illustrate the strategic planning process of a TCA project based on learning outcomes and not to detail the implementation process. Therefore, only the preparation of the final phase of project planning. i.e. the drawing up of the project plan, is outlined below.

From a project management perspective, this is the most important phase, more important than implementation. If it is lagging or weak, managing the project can become difficult. It is quite natural that the TCA officer will probably have to deviate from the plan, but there is a big difference between not having a plan and being clear about what to deviate from as well as the possible consequences of such deviation.

During the project definition phase, the project objective is defined and obtained by breaking down the strategic goals and development objectives that trigger the project. The project objective is specific, the expected learning outcomes have been already assigned (when do we consider the objectives achieved?). Beside this, the evaluation criteria and methods have also been set for measuring the learning outcomes and the expected participants’ profiles are known.

So, this is the time to start planning the actual activities.

The project is made up of elementary activities, however, it is not possible to say where the boundaries of elementary activities lie, since they depend on the nature and organisation of the project. The activity always has a duration and a need for resources. If not, it cannot be called an activity.

It is not possible to say to how many levels an activity should be broken down. It 'depends'. (Two levels may be too few, ten levels may be too many.). The project plan should include all the elementary activities of the project. The direction of the breakdown of activities also depends on the purpose and complexity of the project. It is important that the breakdown is done by a team, not by a single individual.

When planning activities, be aware of the following concepts:

Milestone:

It is a very important event for the progress of the TCA project (e.g. decision, partial product, etc.). The milestone has no duration or units of measure, no indicator and no deadline. Its purpose is to monitor the progress of the project.

Deadline:

Expected fixed date for the completion of the activity, the completion of the product, which may be an internal or external (e.g. contractual) agreement.

Lead time:

The time between the start and end of an activity, that is, the time it takes to complete that certain activity. As a rule, we do not plan on time, but on lead time.

Transit time:

Transit time is the amount of time over which the project manager has no control, you cannot change it, so treat it as a fact. For example, the period of submitting.

Logical connections:

Apart from the start-up phase of the project, all activities have predecessor activities. Therefore, the predecessor activity(s) associated with a given activity must be clearly defined during the planning. The logical connection is usually a Finish-Start, so when an activity ends, the next activity can be started. (For example, if the project plan is ready, you can start the project.)

Time constrains:

Time constraints are the determinants of the timing of the implementation of an activity.

Types of time constraints:

•	ASAP (As Soon As Possible): Start the activity as soon as possible.

This is the most common type of time constraint that is most likely to ensure the success of the project, because if the TCA officer starts an activity right away and for some reason exceeds the planned turnaround time, there is still a big chance that there will be enough spare time to complete the task.

•	ALAP (As Late As Possible): Perform the activity as late as possible.

For example, a bank transfer is contracted out by a subcontractor because the NA has an interest in keeping the money on its bank account.

•	NSET (Not Start Earlier Than): An activity cannot be started prior to…

For example, a project cannot be started until the director's approval has been granted.

•	NFLT (Not Finish Later Than): An activity cannot be started later than…

For example, the technical preparation of the event cannot take place after the arrival of the participants.

•	MSO (Must Start On): You must start the activity at the given time.

For example, the results of the project should be presented at a committee meeting (at a specific time).

•	MFO (Must Finish On): You must complete the activity at that time.

For example, the final task with the participants should be completed at the end of a training session.

Within the above time limits, a project plan can be prepared with using any kind of tool (e.g. organization template, management programmes, etc.).

The bottom line is that all but the first activity should have a predecessor activity, and the activities cover the whole flow of the project.

Guarantees of a successful TCA project

The key issue of a successful TCA project is the thoughtful and thorough preparation.

- Having a clear and universally accepted project objective and measurable learning outcomes

- Management's situational awareness and planning skills

- Well planned implementation activities (what, when, to whom, how, for how much)

- Regular (and not continuous) communication with all key players

- Appropriately selected, trained and supported human resources

- Clear responsibilities and competences

- Feedback of monitoring results

- Effective management of risks and problems

https://ec.europa.eu/education/education-in-the-eu/european-education-area_en

https://salto-et.net/publisher/page/na_directors

Defining, writing and applying learning outcomes – A European Handbook

Cedefop, 2017, p. 31